## Sheet1
One Million NIU Activites, Roles, Hours RELATIONSHIPS SUMMARY
| BUDGET - ACTIVITIES BY SITE 1 - 7 EACH SITE INCURS THESE ACTIVITIES | [7 empty] | Each Site Will Performs These Individual Tasks | CM -Coalition Member | L - Liaison | LT - Lead Trainer | T - Trainer | LAUSD A | LAUSD B | HBUHSD - Huntington Beach Union High School Dist | West Covina USD | Inglewood USD | Inglewood USD | City of Fontana | City of Fontana | Anaheim City School District | [5 empty] | Duarte Unified School District |  |  | Santa Ana Unified School District |  |  | Huntington Beach | Pomona School District | [5 empty] | Pomona School District |  | Pomona School District | [10 empty] | Duarte USD |  |  | LAUSD | LAUSD | LAUSD | LAUSD | LAUSD | LAUSD/East LA | [10 empty] | Anaheim City School District | [5 empty] | Inglewood USD |  |  |  | West Covina USD | Covina Valley USD |  |  |  | Montebello USD |  | San Fernando Valley | APCH
Hours Req'd to Complete Task | I | II | III | IV | V | VI | VII | [6 empty] | 1 | 2 |  |  | 1 | 2 |  |  | Superintendent Linda Wagner (714) 517-7510 lkwagner@acsd.us Yesenia Navarro Curriculum Spec Community Involvement Elementary Dist Contact ynavarro@acsd.k12.ca.us 714-517-7530 ext 4108 | [5 empty] | Kevin Morris is now PUSD comunnity Liason - kmorris@duarte.k12.ca.us huge promotion 626-599-5130, cell: 626-841-3376 | [5 empty] | Amy will be looking at the MOU and we might start classes in Jan 2015 | Cluster 3 - Lead Agent Jennifer Francev - Ganesha High Principal - patty- office mgr | [18 empty] | Kevin Morris is now PUSD comunnity Liason - huge promotion 626-599-5130, cell: 626-841-3376 |  |  | 1 | 2 | 3 | 4 | 5 | [11 empty] | Yesenia Navarro Curriculum Spec Community Involvement Elementary Dist Contact ynavarro@acsd.k12.ca.us 714-517-7530 ext 4108 |  |  |  |  | Adriana Martin del Campo
10 | 1 | 1 | [5 empty] | 1 | Sites | 1 | 1 |  |  | Bethune Middle School 155 W. 69th St. Los Angeles, Ca 90003 | Bethune Middle School 155 W. 69th St. Los Angeles, Ca 90003 | OceanView High School HBUHSD | Hollencrest Middle School 2101 E Merced Ave, West Covina, CA 91791 | Inglewood (Parent Center) 401 S. Inglewood Ave Inglewood, Ca. 90301 | Inglewood (Parent Center) 401 S. Inglewood Ave Inglewood, Ca. 90301 | Cypress Center 8380 Cypress Ave, Fontana, Ca 92335 AM Session | Cypress Center 8380 Cypress Ave, Fontana, Ca 92335 PM Session | Thomas Jefferson Elementary 504 E. South Street Anaheim CA 92805 | Palm Lane Elementary School 1646 W. Palm Lane Anaheim CA 92802 US | Edison Elementary School 1526 E. Romneya Drive Anaheim CA 92805 | Henry Elementary School 1123 W. Romneyro Drive, Anaheim, CA 92801 | Lincoln Elementary 1413 E Broadway Anaheim CA 92805 ¦ Phone: 714-517-8929 | Horace Mann Elementary School 600 W. La Palma Ave. Anaheim CA 92801 ¦ Phone: 714-517-8938 | Northview Inter Rick Crosby | Duarte High School | Mt. Olive | Saddleback HS- 2802 South Flower St Santa Ana, CA 92707 | PUSD- Emerson Middle School- 635 Lincoln Ave Pomona, CA |  | Oak View (Library) | Kellogg Ele 610 Medina St. Pomona, Ca 91768 | Arroyo Ele 1605 W. Arroyo Ave. Pomona, Ca 91768 | Roosevelt Ele 701 N. Huntington Blvd. Pomona, Ca 91768 | Cortez Math and Science Magnet School | Ganesha | Marshall | Lexington Elem 550 W. Lexington Ave, Pomona, Ca 91766 | Garey High School | Madison Elementary | Vejar Elementary | Lopez Elementary | Fremont High School Academy of Engineering & Design | PUSD- Emerson Middle School- 635 Lincoln Ave Pomona, CA | Village Academy HS | Simons M.S. 900 E. Franklin Ave. Pomona, Ca 91766 | Washington | Golden Springs | Lincoln Elementary | Devry University Pomona | Royal Oaks Elem- | Maxwell-Principal Dr. Kelly | Andres Duarte Rick Crosby | 1st Street Elementary | Main Street Elementary | Marianna Elementary | Esteban Torres High School | Hilda Solis School | Santee Ed. Complex 1921 Maple Ave. Los Angeles, Ca 90011 | Rowan Avenue Elementary 600 S. Rowan Avenue, Los Angeles, CA 90023 | Hawaiian Elementary 540 Hawaiian Ave, Wilmington, CA 90744 | Nimitz Middle School 6021 Carmelita Ave, Huntington Park, Ca 90255 | MacArthur Park Ele 2300 W. 7th St. Los Angeles, Ca 90057 | PACE- Community Volunteer Coordinator, PACE Early Childhood Education | East LA YC 4360 Dozier St, Los Angeles, CA 90022 | Esteban Torres High School | Hilda Solis School | Bridge Elementary School | 1st St. Elementary - EAST LA OFFICE SITE | ACSD- Westmont Elementary 1525 W Westmont Dr, Anaheim, CA 92801 | ACSD- Roosevelt Elementary School 1600 E. Vermont Ave. Anaheim CA 92805 | Valley High School | Madison Elementary 1124 Hobart St, Santa Ana, Ca 92707 | Sierra Intermediate 2021 N. Grad Ave, Santa Ana, Ca 92705 | Jefferson Elementary | Inglewood (Parent Center) 401 S. Inglewood Ave Inglewood, Ca. 90301 | Highland Elementary | Kelso Elementary | Morningside High 10500 S Yukon Ave, Inglewood, CA 90303 | Monte Vista Elementary | Lark Ellen Elem- CVUSD 4555 N. Lark Ellen Ave., Covina, 91722 | Cypres Elementary - CVUSD | Las Palmas Middle School, 611 No. Larkellen Ave. ,Covina, Ca. 91722 | Northview High School 1016 W Cypress S, Covina, Ca 91722 | Montebello Unified- Applied Technology Center (ATC) 1200 W. Mines Ave., Montebello, CA 90640 | Montebello USD- Suva Intermediate- | El Proyecto del Barrio Worksource 9024 Laurel Canyon Blvd.Sun Valley, CA 91352 | A Place Called Home 2830 S. Cemtral Ave Los Angeles, Ca 90011 | ACSD- Betsy Ross Elementary- 535 South Walnut Street, Anaheim, CA 92802
2 |  | 1 | 1 |  |  |  |  | 2 | Contact Info | 1 | 1 |  |  | Community School Coordinator Ms. Jennifer Reid 323-541-1800 ext. 8023 jreid@laep.org Jen's cell 626-827-7252 Ciani - jennifer asst. 323-541-8023 Carlos Gonzalez Principal cxg0564@lausd.net Parent Liason: , 213-280-5925, Lorena Herrerra, ciani - cnunezmurillo@laep.org 323-541-1874 | Community School Coordinator Ms. Jennifer Reid jreid@laep.org Jen's cell 626-827-7252 Ciani - jennifer asst. 323-541-1830 Carlos Gonzalez Principal cxg0564@lausd.net Parent Liason: Patricia Navarro navarro5935@gmail.com parent center 323-541-1800 ext. 8023, 213-280-5925, Lorena Herrerra, ciani - cnunezmurillo@laep.org 323-541-1874 | Shawn Werner swerner@hbuhsd.edu | Principal Hector Galicia 626-931-1760 hGALICIA@wcusd.org Zaida Gonzales zgonzalez@wcusd.org office asst | Monica Hernanez mhernandez@inglewood.k12.ca.us 310-419-2788 |  | Eydee Jimenez ejimenez@fontana.org 909-349-6987 FUSD: Silma Navarro NavaSV@fusd.net 909) 357-7600, ext. 29318 | Eydee Jimenez ejimenez@fontana.org 909-349-6987 FUSD: Silma Navarro NavaSV@fusd.net 909) 357-7600, ext. 29318 | Principal Yadira Moreno ymoreno@acsd.us Yamile Forero ycanon@acsd.k12.ca.us 714.285.3700 Community Liaison Thomas Jefferson School | Principal Tracey Golden - tgolden@acsd.us - Community Liaison - Maria Sanchez - msanchez@acsd.k12.ca.us - Phone: 714-517-8944 | Principal Sandoval - psandoval@acsd.k12.ca.us - Community Liaison - Marisol Cordova mcordova@acsd.k12.ca.us - Phone: 714-517-8902 | Principal Beatriz Garcia - bgarcia@acsd.us - bgarcia@acsd.k12.ca.us - Community Liaison Daniel Boyzo - dboyzo@acsd.k12.ca.us (714) 517-8914 | Principal Tammie Ledesma tledesma@acsd.us Diana Zapata 714-517-8929 ext. 2091 dzapata@acsd.k12.ca.us | Principal Dr Amanda Segovia asegoviahale@acsd.k12.ca.us Community Liason: Guillermina Galindo 714-517-8938 ggalindo@acsd.k12.ca.us | Rick Crosby rcrosby@duarteusd.org 626-599-5600 nina thompson office manager nthompson@duarteusd.org | Principal Mark Sims MSims@duarteusd.org 626-599-5702 mbradley@duarteusd.org - Marilyn Bradley Office Manager | Principal Luis haro lharo@duarteusd.org 626) 599-5902 | Dr. Robert Laxton Robert.laxton@sausd.us, Parent Liaison: carolina.gonzalez@sausd.us (714) 569-6300 | Coordinator Ashley Hedrick ashley.Hedrick@pomona.k12.ca.us, carmen.scott@pusd.org 909-397-4516 Maria Martinez Resource Teacher Emerson Middle School 909-397-4516 |  | Amy Crepeau Literacy Volunteers-HBPL Family Literacy Program (714) 375-5104 hrs 9-12 & 4-8 crepeaua@hbpl.org | Rabia Minhas rabia.minhas@pusd.org 909-397-4604 | Principal Claudia Ruiz claudia.ruiz@pusd.org 909-397-4568 | Principal Villa - Alejandro.villa@pusd.org Jannell Baldanado- off mgr. 909-397-4667 | Lisa Minami-Principal (909) 397-4750 lisa.minami-lin@pusd.org | jennifer.francev@pusd.org 909-397-4400 | Principal Juan Ortiz juan.ortiz@pusd.org (909) 397-4532 | Silvestre Maravilla silvestre.maravilla@pusd.org 909-397-4616 beatrice.torrez@pusd.org - Julieta.mendoza@pusd.org | , Garey High Teacher - Ion Puschia Ion.puschia@pusd.org | Principal Ana Rico - 909-397-4643 anna.rico@pusd.org | Principal Terry Walker 909-397-4985 terry.walker@pusd.org | Principal Jesus Peralta 909-397-4438 jesus.peralta@pusd.org | Principal Elizabeth Harper 909-397-4521 elizabeth.harper@pusd.org | Coordinator Ashley Hedrick ashley.Hedrick@pomona.k12.ca.us, carmen.scott@pusd.org 909-397-4516 Maria Martinez Resource Teacher Emerson Middle School 909-397-4516 | New principal - | Cristine Goens cristine.goens@pusd.org Isabel.arraraz@pusd.org 909-397-4544 |  |  |  |  | Principal JaniceKolodinski 626/599-5400 jKolodinski@duarte.k12.ca.us | 626-599-5301 "kbuckley@duarte.k12.ca.us | direct line: 626-599-5101 rcrosby@duarte.k12.ca.us | Maria Martinez 323-269-0138 | Jessica Trejo - Title 1 Coordinator Jlt2912@lausd.net 323-232-4856 | Estella Campos 323) 262-6382 ecampo6@lausd.net |  |  | Ms. Maritza Martinez Asst. Principal mam8628@lausd.net 213-763-1000 | gmartinez@utla.net, Parent Rep Mari Flores: mxf8139@lausd.net, IT person: alfredo.viramontes@lausd.net (323) 261-7191, Mari Parent Rep cell: 323-272-9545, Gloria cell: 626-482-0513 | Luis Rivera lriver2@lausd.net, 310-830-1151 | Juan Perez jperez2174@gmail.com, Amparo Mendoza axm8519@lausd.net direct line 323-887-5484, off 323-887-5401 Principal Miguel Saenz | Karen Leon, Luis Velasco lvelas2@lausd.net, kdl5159@lausd.net 213-381-7217 - Parent Alumni- SSC Member-Diana Guillen 213-822-4366 | Brenda Sandoval BPerez@pacela.org |  | Community Liason |  | Alex Martinez axm6341@lausd.net |  | Lucia Bernal, Leslie Pelegrina-Principal lbernal@acsd.k12.ca.us, lbernal@acsd.us, lperegrina@acsd.us 714-517-8965 | lperegrina@acsd.k12.ca.us, (Rafaela Moraza) rmoraza@acsd.k12.ca.us, Sally Astacio-Carbonell <sastacio-carbonell@acsd.k12.ca.us>, Noemy Penilla <npenilla@acsd.k12.ca.us> | Principal Patrick Yrarrazaval-Correa, Liason - Lizbeth Padilla Lizbeth.Padilla@SAUSD.US, patrick.yrarrazaval@sausd.us, jeffrey.rozema@sausd.us, princ secretary: connie.santos@sausd.us Patrick: 714-241-6400, c: 714-315-7742; Jeff:714-241-6402, cell: 714-322-8222 | Ramona Alvarez alvarezramona08@yahoo.com 714.972.6400 Principal Ana Gonzalez: ana.gonzalez@sausd.us asst name: Cuca | Lori Cervantes lori.cervantes@sausd.us 714) 567-3500 |  | Monica Hernanez mhernandez@inglewood.k12.ca.us 310-419-2788 |  |  | Nicole Trimble, ntrimble@inglewood.k12.ca.us, 310-680-5230 | LiliaGonzalez-Gomez(626) 939-4830 lggomez@wcusd.org | Principal Judy Gonzales 626-974-4510 |  | 626-974-7200, | 626-974-6120, | Jose, Ornelas Peregrina, Estela <Peregrina_Estela@montebello.k12.ca.us, Ornelas, Jose <Ornelas_Jose@montebello.k12.ca.us> (323) 248-2500 | Principal Teresa Alonso o: 562-806-7820, cell: 3239474631 alonzo_teresa@montebello.k12.ca.us, kline_julie@montebello.k12.ca.us | Shakeh, Nancy smanookian@wscalnetwork.org, nmacias@wscalnetwork.org | Ana Maria anamaria@apch.org 323-232-7653 Ext: 2239 | New Principal Trisha Graper tgraper@acsd.us Community Liaison Beatriz Zavala (714) 517-2993 . bzavala@acsd.k12.ca.us
2 |  |  | 1 | 1 |  |  |  | 3 | Parent Lead Contact |  | 1 |  |  |  | Sandra De Los Santos, Eloisa Gomez, Ana Laura, Rodriguez, Roberto Aguirre, Azucena Alvarado, Beatriz Diaz, Evangelina Muñoz, Imelda Palacios, Carmen Quijada, Lucia Romero, Noemi Rivas | Caritina Gaspar (714) 955-9737 - Juan Vargas (dad) & Luz Maria Ruiz (mom) – 714-596-7511 Irene Fuentes – (714) 844-3843 | 9/25: Mr, Galicia did not want to share contact info -Mr. Galicia will ask his PTSA committee if they want to contacted by us, will find out 0n 9/24 |  |  | Brandy Segull - Parent Connect - | [14 empty] | Patricia Valencia |  | marisaporras@gmail.com 909-927-0189 - Roosevelt Alumni | Lee Moore-Parent Leader (PTSA) 714-401-3880 | Rosa NIU Trainer | Rosa NIU Trainer, Marissa Porras NIU Roosevelt Alumni | Marta Ulloa - NIU Trainer 909-326-9385 | Claudia Bedolla SSC - Parent Community Rep 909-236-8945 claudia.bedolla78@gmail.com | [5 empty] | Elvira - NIU Trainer |  |  | Leticia Velasquez - Alumni Roosevelt velaszquezl145@gmail.com 909-229-6235 | Fede Guerrero 909-837-9549 | [5 empty] | Sonia Rodriguez |  |  |  | Adella Salazar |  |  |  | Diana Guillen | [13 empty] | NIU Trainer - Maria Brito | NIU Trainer- Lilia Estrada
3 |  |  |  | 1 | 1 | 1 | 1 | 4 | Schedule |  | 1 | 1 |  | Tue, Th (3 hrs) 9-12pm | Tue, Th (3hrs) 4-7 pm Room C-32 | AM - Tues, Thur (Two) PM - Tues, Thur 8:30-10:30 AM & 6-8PM | Tues, Thur PM 6-8 | M, W 9-12:30 | T, Th 9-12:30 | Tues, Thurs AM - 9-12 | Tues, Thurs PM 5-8 | T: 2-5pm W:1-4pm | T/Th 2pm-5pm | M/W 8:15-11:15am | T/Th 4:30pm-7:30pm | M,W 5-8pm | M/W 3pm-6pm | T, W, Th 3-6 pm | T, W, Th 3-6 pm | T,W, Th 2-5 pm | Morning session 9-11am & Evening 6:00PM-8:00PM | Thursdays/Fridays 9:00am-11:00am and 2:30pm-4:30pm |  | Wed, Fri 9-12 | Monday/Wed 4-6pm | Tues/Thurs 6-8pm | Tues/Thur 4-6pm | Tues/Thur 9am-12pm |  |  | Tue, Th 3 hrs 9-12am | TBA |  |  |  |  | Thursdays/Fridays 9:00am-11:00am and 2:30pm-4:30pm | [5 empty] | Mon, Wed, Fri (3.5 hrs) | [8 empty] | Tue, Th (3 hrs) | Wednesdays/Thursdays 11:30am-2:30pm |  | Tue, Th (3 hrs) | Tue, Th (3 hrs) | Mon-Fri (9-12:30) | [6 empty] | Tues/Thurs 5:00PM-7:30PM |  |  |  |  | Tue, Wed, Thur (3.5 hrs)
1 |  |  |  | 1 | 1 | 1 |  | 5 | Type of Class | 1 | 1 | 1 |  | QSTE | QSTE 2 | QSTE | QSTE | PE+T | PE+T | QSTE |  | PE+T | PE+T | PE+T | PE+T | PE+T | PE+T | TRP Youth | TRP Youth | TRP Youth | PE+T | QSTE |  | QSTE | QSTE | QSTE | QSTE |  |  | QSTE | PE+T | QSTE | Per LO, waiting on school contact info | Per LO, waiting on school contact info | Per LO, waiting on school contact info | Per LO, waiting on school contact info | QSTE | [5 empty] | QSTE |  |  |  |  | QSTE |  |  |  | QSTE | PE+T | QSTE | QSTE | QSTE | QSTE |  |  |  |  | QSTE | PE+T | QSTE |  |  |  |  | QSTE |  |  |  | PE+T or QSTE | QSTE | [5 empty] | QSTE | QSTE | Train the Trainer
4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | MOU SENT | 1 | 1 |  |  | 8/27/14 $2,700 |  | 8/21/2014 $10,800 | Sent 8/28/14 $2,700 | MOU sent 9/5/14 |  | 9/9- LO sent signed contract 9/9/14 |  | MOU sent 9/9/14 DJ $21,900 | [5 empty] | MOU sent 9/11/14 |  |  | MOU sent 10/9/14 | Resend corrected MOU 10//17/14 |  | MOU sent 9/17/14 | MOU sent 9/3/14 - DJ $10,800 | [5 empty] | Sent 8/25/2014 $5,700 | Waiting on LO | [47 empty] | 10/14: LO sent ExecSumm and video link to John Alvarz contact @ El Proyecto, he will be visting with principal, Ms. herran Sun VAlley High School. | MOU sent 9/10/14 $1,350 | Mou sent 9/5/14 $2,700 - Denied, Not in Budget but will host Train the Trainer & will try to get some of their parents to particpate inYesenias schools.
4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | MOU SIGNED | 1 | 1 | [6 empty] | 2014-09-18 | 2014-09-18
1 |  |  | 1 | 1 | 1 |  |  | 8 | Target Enrollment | 1 | 1 |  |  | 15 | 15 | 120 | 30 | 15 | 15 | 12 | 12 | 18 | 18 | 18 | 19 | 19 | 19 | 15 | 15 | 15 | 30 | 30 | 390 | 12 | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 |  |  |  |  | 20 | 20 | 20 | 15 | 15 | 15 |  |  | 15 | 30 |  | 30 | 15 |  | 30 | [7 empty] | 15 | 15 |  | 15 | [13 empty] | 0
2 |  |  |  |  | 1 | 1 |  | 9 | Actual Enrollment | 1 |  | 1 | 1 | 17 |  | 90 |  | 10 | 18 | 5 |  | 24 | 18 | 26 | 25 | 26 | 27 | 16
2 |  |  | 1 | 1 |  |  |  | 10 | Ask school contact to provide a list of 200 to 400 parents (100 for every 5) (target/5X100) |  |  | 1 |  | 300 | 300 | 2400 | 600 | 300 |  | 240 |  | 162 | 162 | 162 | 171 | 171 | 171 | 150 - Is relunctant to give list, has 90 students in their after school program, would like to involve those students. | 150 | No - List, they only have 60 students, will offer extra credit for class for incentive. |  |  |  | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | [48 empty] | #VALUE!
2 |  |  | 1 | 1 |  |  |  | 11 | Up Coming Events |  | 1 | 1 |  |  |  |  | Tues 10/7 Mailer at site @ 1pm. Thu 10/16 Parent Conferences 5:30pm-7:30pm |  | Maria Zepeda will go to Back to School Night at Centinela Ele @ 9/25 5-6pm & Highland Ele @ 10/1 5-6pm
2 |  |  |  |  | 1 | 1 |  | 12 | IT Visit Scheduled |  |  | 1 | 1 | 8/28/14 - Juan Carlos |  | 8/26/14 - Juan |  | n/a |  | NR 8/12/2014
2 |  |  |  |  | 1 | 1 |  | 13 | IT VISIT Complete |  |  | 1 |  | Done |  | Done | Done |  |  | Done | [13 empty] | Done
2 |  |  |  |  | 1 | 1 | 1 | 14 | Trainers | 1 |  | 1 | 1 | Julio, Esteban | Yuliana, Esteban | Adriana | Joacim, Maggie | Maria Juan Carlos | Maria Juan Carlos | Veronica Murrillo |  | Julio Manuel | Alvaro Angela | Elfy Manuel | Araceli Alvaro | Beatriz Araceli | Angela Alvaro | Juan Lopez | [5 empty] | Adriana | Elvira, Rosa | Esperanza, Cecilia Vazquez | Mariac Chavira, Francel (T+T2) | Irene Braha, Fracel (T+T1) |  |  | Esperanza, Marta, Milagros | [11 empty] | Marta, Esperanza | [10 empty] | Alvaro |  |  | Teresa | [5 empty] | Adriana, Oztoc | [5 empty] | Liliana, Marta | [8 empty] | Yuliana, Alvaro |  |  | Hortensia, Silvia
1 |  |  |  |  | 1 |  |  | 15 | Back Up Trainer |  |  | 1 | 1 | Yuliana | Julio | Elfie |  |  |  | Train the Trainer | [13 empty] | Adriana | [6 empty] | Rosa | [11 empty] | Rosa | [19 empty] | Gloria Iwaki
4 |  |  |  |  | 1 | 1 | 1 | 16 | Actual Grads |  |  | 1 | 1 | 17
3 |  |  | 1 | 1 |  |  |  | 17 | Orientation Date |  |  | 1 | 1 | 2014-09-09 | 2014-10-14 | 2014-10-02 | 2014-10-14 | 2014-10-06 | 2014-10-07 | 2014-10-07 |  | 2014-10-07 | 2014-10-14 | 2014-10-15 | 2014-10-14 | 2014-10-09 | 2014-10-16 | 2014-10-14 | 2014-10-21 | 2014-10-21 |  |  |  | 2014-10-01 | 2014-10-06 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | [19 empty] | 2014-09-09 |  |  | 2014-09-09 | 2014-09-09 | [24 empty] | 2014-10-07
2 |  |  | 1 | 1 |  |  |  | 18 | Orientation Shows |  |  |  | 1 | [9 empty] | 16 |  | 38
1 |  |  | 1 | 1 |  |  |  | 19 | Orientation Time |  |  | 1 | 1 |  | 3-4 pm |  | 18:00 |  |  |  |  | 8:30 | 14:00 | 8:30 | 17:00 | 17:30 | 15:00 | 16:30 | 16:00 | 14:00
1 |  |  |  | 1 | 1 |  |  | 20 | Start Date |  | 1 | 1 | 1 | 2014-09-09 | 2014-10-21 | 2014-10-07 | 2014-10-21 | 2014-10-13 | 2014-10-14 | 2014-10-16 | 2014-10-21 | 2014-10-14 | 2014-10-16 | 2014-10-20 | 2014-10-16 | 2014-10-13 | 2014-10-20 | 2014-10-16 | 2014-10-28 | 2014-10-28 |  |  |  | 2014-10-08 | 2014-10-06 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-07 | 2014-10-14 | 2014-10-14 | [19 empty] | 2014-09-09 |  |  | 2014-09-09 | 2014-09-09 | [24 empty] | 2014-10-07
1 |  |  |  |  | 1 | 1 |  | 21 | End Date |  | 1 | 1 |  | 2014-09-25 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-05 | 2014-11-06 | 2014-11-06 | 2014-11-13 | 2014-12-03 | 2014-12-04 | 2014-12-03 | 2014-11-20 | 2014-12-03 | 2014-11-25 | 2014-11-13 | 2014-11-13 | 2014-11-13 |  |  |  | 2014-10-29 | 2014-11-05 | 2014-11-06 | 2014-11-06 | 2014-11-06 | 2014-11-06 | 2014-11-06 | 2014-11-18 | 2014-11-18 | [19 empty] | 2014-09-25 |  |  | 2014-09-25 | 2014-09-25 | [24 empty] | 2014-11-06
2 |  |  |  |  | 1 | 1 |  | 22 | Grad Date | 1 | 1 | 1 |  | 2014-10-02 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-18 | 2014-11-18 | 2014-11-20 | 2014-11-20 | 2014-12-09 | 2014-12-11 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-04 | 2014-11-18 | 2014-11-18 | 2014-11-18 |  |  |  | 2014-11-05 | 2014-11-12 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-20 | 2014-11-20 | [19 empty] | 2014-09-30 |  |  | 2014-09-30 | 2014-09-30 | [24 empty] | 2014-11-18
1 |  |  |  |  | 1 | 1 |  | 23 | Grad Time | 1 | 1 | 1 |  | @ 10am | @11am | 18:00 |  |  |  | @ 6pm | @ 6pm | @3pm | @3pm | @10am | @5:30pm | @6pm | @5pm | Combo Grad @ 5pm
1 | [6 empty] | 1 | 24 | Last Quarter Grad # |  |  | 1 |  | 30 |  |  |  | 10 | [12 empty] | 42 | 21 |  |  | 11 | 12 | 12 | 12 |  |  | 32 | [5 empty] | 21 |  | 23 |  |  |  | 22 | [8 empty] | 20 | 20 | 5 | 24 | 10 | 12 | [5 empty] | 22 | 21 |  |  |  |  | 10 |  |  |  |  | 10 |  |  |  | 14 |  | 16
10 | [6 empty] | 1 | 25 | Train the Trainer Session | 1 | 1 | 1 |  | N/A | N/A | Train the Trainer - @ HB Start Date Wed. 9/12/14 9am-1pm End Date Wed. 9/26/14 |  |  |  | N/A | [13 empty] | Train the Trainer - @ HB Start Date Wed. 9/12/14 9am-1pm End Date Wed. 9/26/15 | [6 empty] | Devry University- Start Date: 9/15/2014, End Date: 10/3/2014 Monday, Wednesday, and Friday 9am-1pm | [50 empty] | Train the Trainer - Start Date Wed. 9/17/14 5-7pm End Date Wed. 10/1/14 Computer Lab, ROOM 15.
2 |  | 1 | 1 | 1 |  |  |  | 26 | Dead Line to get List of Parent contact info (Name, Home address, phone number in excel format) | 1 | 1 | 1 |  | 2014-08-27 | 2014-10-03 | 2014-09-10 | 2014-09-24 | 2014-09-16 |  | 2014-09-27 |  | 2014-10-04 | 2014-10-11 | 2014-10-12 | 2014-10-11 | 2014-10-06 | 2014-10-13 | n/a see above line 10 for details | 2014-10-04 | n/a see above line 10 for details |  |  |  | 41893 | 2014-09-16 | 2014-09-17 | 2014-09-17 | 2014-09-17 | 2014-09-17 | 2014-09-17 | 2014-09-17 | 2014-09-17 | [19 empty] | 41871 |  |  | 41871 | 41871 | [24 empty] | 2014-09-17
2 |  |  | 1 | 1 |  |  |  | 27 | Received Parent Database |  | 1 | 1 |  |  | Not yet, their system is down | Yes
1 |  |  | 1 | 1 |  |  |  | 28 | *or school provided labels to have mailers done on site. (Yes or No Answer) |  | 1 | 1 |  |  |  |  | Maybe: He wants to send a flyer home with a return receipt to the school |  |  | 360
2 |  |  | 1 | 1 |  |  |  | 29 | Trainers scheduled to do the Mailer. (folding, stuffing and labeling) (What is the date) | 1 |  | 1 | 1 | 2014-09-02 | 2014-10-07 | 2014-09-14 | 2014-09-28 | 2014-09-20 |  | 2014-10-01 |  | 2014-09-30 | 2014-10-07 | 2014-10-08 | 2014-10-07 | 2014-10-02 | 2014-10-09 | 2014-09-28 | 2014-10-08 | 2014-10-05 |  |  |  | 2014-09-15 | 2014-09-20 | 2014-09-21 | 2014-09-21 | 2014-09-21 | 2014-09-21 | 2014-09-21 | 2014-09-21 | 2014-09-21 | [19 empty] | 41873 |  |  | 41873 | 41873 | [24 empty] | 2014-09-21
4 |  |  | 1 | 1 |  |  |  | 30 | Date Mailer Sent (2 Wks before Orientation Date) |  |  | 1 | 1 | 2014-09-03 | 2014-10-07 | 2014-09-16 | 2014-09-30 | 2014-09-22 |  | 2014-10-03 |  | 2014-10-02 | 2014-10-09 | 2014-10-10 | 2014-10-09 | 2014-10-04 | 2014-10-11 | 2014-09-30 | 2014-10-10 | 2014-10-07 |  |  |  | 2014-09-17 | 2014-09-22 | 2014-09-23 | 2014-09-23 | 2014-09-23 | 2014-09-23 | 2014-09-23 | 2014-09-23 | 2014-09-23 | [19 empty] | 41877 |  |  | 41877 | 41877 | [24 empty] | 2014-09-23
1 |  |  | 1 | 1 |  |  |  | 31 | Emailed school All Call script File Name: |  |  | 1 |  | 2014-08-30 | 2014-10-08 | 2014-09-26 | 2014-10-08 | 2014-09-30 |  | 2014-10-01 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-08 | 2014-10-15 | 2014-10-15 |  |  |  | 2014-09-25 | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | [48 empty] | 2014-10-01
1 |  |  | 1 | 1 |  |  |  | 32 | Initial All Call Date - One week before |  | 1 | 1 |  | 2014-09-03 | 2014-10-08 | 2014-09-26 | 2014-10-08 | 2014-09-30 |  | -6 |  | 2014-10-03 | 2014-10-10 | 2014-10-11 | 2014-10-10 | 2014-10-05 | 2014-10-12 | 2014-10-08 | 2014-10-15 | 2014-10-15 |  |  |  | 2014-09-25 | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | [48 empty] | -6
1 |  |  | 1 | 1 |  |  |  | 33 | Initial All Call Follow Up |  | 1 | 1 |  | 2014-09-08 | 2014-10-13 | 2014-10-01 | 2014-10-13 | 2014-10-05 |  | 2014-10-06 |  | 2014-10-10 | 2014-10-12 | 2014-10-16 | 2014-10-12 | 2014-10-09 | 2014-10-16 | 2014-10-13 | 2014-10-20 | 2014-10-20 |  |  |  | 2014-09-30 | 2014-10-05 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | [48 empty] | 2014-10-06
1 |  |  | 1 | 1 | 1 |  |  | 34 | Reminder All Call Date |  | 1 | 1 |  | 2014-09-06 | 2014-10-11 | 2014-10-01 | 2014-10-13 | 2014-10-05 |  | 2014-10-04 |  | 2014-10-06 | 2014-10-13 | 2014-10-14 | 2014-10-13 | 2014-10-08 | 2014-10-15 | 2014-10-13 | 2014-10-20 | 2014-10-20 |  |  |  | 2014-09-30 | 2014-10-05 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | [48 empty] | -1
2 |  |  | 1 | 1 | 1 |  |  | 35 | Mailer & Supply Budget submitted to LO-Date: | 1 |  | 1 |  |  |  | 2014-09-15
3 |  |  |  | 1 | 1 |  |  | 36 | First Follow Up Call from Mailer- Llamada Seguimiento de las cartas que mandamos |  |  | 1 | 1 | 2014-09-02 | 2014-10-10 | 2014-09-23 | 2014-10-12 | 2014-10-02 |  | 2014-09-30 |  | 2014-09-30 | 2014-10-07 | 2014-10-08 | 2014-10-07 | 2014-10-02 | 2014-10-09 | 2014-10-07 | 2014-10-14 | 2014-10-14 |  |  |  |  | 2014-09-29 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-09-30 | [50 empty] | 2014-09-30
2 |  |  |  | 1 | 1 |  |  | 37 | Reminder Follow Up from Mailer - Llamada Recerdatorio |  |  | 1 | 1 | 2014-09-08 | 2014-10-13 | 2014-10-01 | 2014-10-13 | 2014-10-05 |  | 2014-10-06 |  | 2014-10-06 | 2014-10-13 | 2014-10-14 | 2014-10-13 | 2014-10-08 | 2014-10-15 | 2014-10-13 | 2014-10-20 | 2014-10-20 |  |  |  |  | 2014-10-05 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | 2014-10-06 | [48 empty] | 2014-10-06
1 |  |  |  | 1 |  |  |  | 38 | Who will do the Follow-Up Call |  |  | 1 |  | Hortencia | Hortencia | Hortencia | Hortencia | Trainers |  | Hortencia |  | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers |  |  |  | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | Trainers | [48 empty] | Trainers
2 | [5 empty] | 1 |  | 39 | Email letter script and Flyer to Alumni (use alumni database)- Llamada al alumnos y email flyer al alumnos |  |  | 1 | 1 | 2014-08-30 | 2014-10-10 | N/A | 2014-10-05 | 2014-09-26 |  | 2014-09-28 |  | 2014-09-27 | 2014-10-04 | 2014-10-05 | 2014-10-04 | 2014-09-29 | 2014-10-06 | 2014-10-04 | 2014-10-11 | 2014-10-11 |  |  |  |  | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | [48 empty] | 2014-09-27
1 | [6 empty] | 1 | 40 | Committees Members | 1 |  | 1 | [5 empty] | Liliana, Maria | [22 empty] | Martha | [23 empty] | Hortencia, Sylvia | [13 empty] | Liliana, Maria
2 | 1 | 1 | 1 |  |  |  |  | 41 | Plan to Contact PTA, Title 1 and School Site Council Representative, Schedule Presentation to their earliest meeting | 1 |  | 1 |  | 2014-08-30 |  | 2014-09-22 | 2014-10-04 | 2014-09-26 |  | 2014-09-27 |  | 2014-09-27 | 2014-10-04 | 2014-10-05 | 2014-10-04 | 2014-09-29 | 2014-10-06 | 2014-10-04 | 2014-10-11 | 2014-10-11 |  |  |  |  | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | [48 empty] | 2014-09-27
2 | 1 | 1 | 1 |  |  |  |  | 42 | PTA, ELAC,Delac, SSC Contact Person | 1 |  | 1 |  | Bethune alumni : imeldapalacios17272gmail.com 323-677-8670 323-750-4475 | Bethune alumni : imeldapalacios17272gmail.com 323-677-8670 323-750-4475 | [26 empty] | Claudia Bedolla - SSC Member Parent Center 909-397-4451 ext. 2310 : Marielena Ayala & Ronnie York |  |  | Maria A. Garcia- District Parent Involvement | [10 empty] | Silvia AlonsoCervantes- PTSA | [8 empty] | Melissa Meza, Title 1/ELL Coordinator 323) 887-5400 | Diana Guillen, NIU Alumni, SSC member 213) 822-4366
1 | 1 | 1 | 1 |  |  |  |  | 43 | PTA, ELAC,Delac, SSC Contact Person Date last Contact | 1 |  | 1 |  | 2014-09-15 | 2014-09-15
2 | 1 | 1 | 1 |  |  |  |  | 44 | PTA, ELAC,Delac, SSC, School Board Next Mtg | 1 |  | 1 |  | Back to School Nite Presentation | [20 empty] | 9/10/14 8:30am - 10:30am PARENT LEADS MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA 8:30am - 10:30am | 9/10/14 8:30am - 10:30am PARENT LEADS MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA 8:30am - 10:30am | 9/10/14 8:30am - 10:30am PARENT LEADS MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA 8:30am - 10:30am | 9/10/14 8:30am - 10:30am PARENT LEADS MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA 8:30am - 10:30am |  |  | 9/23: Title 1 meeting @8:30am: Esperanza and other parents will be going to this meeting to ask for the computer class. 9/10 BOARD MTG -7:30 pm Education Center Board Room: 800 S. Garey Ave. Pomona CA | 9/10/14 8:30am - 10:30am PARENT LEAD MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA 9/19/14 - 8:30am TITLE 1 & BAC Parent MTG -Garey HS Library | 10/8/14 8:30am - 10:30am PARENT LEADS MTG Education Center's Strategic Room: 800 S. Garey Ave. Pomona CA
1 | 1 | 1 | 1 |  |  |  |  | 45 | Actual Date Contact PTA, Title 1 and School Site Council Representative | 1 |  | 1 |  |  | They are bearly going to have their elections this week
2 | 1 | 1 | 1 |  |  |  |  | 46 | Email Flyer to PTA, Title 1 and School Site Council |  | 1 | 1 |  | 2014-08-30 |  | 2014-09-22 | 2014-10-04 | 2014-09-26 |  | 2014-09-27 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-04 | 2014-10-11 | 2014-10-11 |  |  |  |  | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | [48 empty] | 2014-09-27
2 | 1 | 1 | 1 |  |  |  |  | 47 | Posting a Flyer using #onemillinniu @ NIU Facebook, E-Team Facebook, Trainer's Facebook, Parent Leader Facebook, NIU Webpage, | 1 | 1 | 1 | 1 |  |  | 2014-09-30 | 2014-10-04 | 2014-09-26 |  | -10 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-04 | 2014-10-11 | 2014-10-11 |  |  |  |  | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | [48 empty] | -10
3 | 1 | 1 | 1 |  |  |  |  | 48 | Create and Email Flyer to school |  | 1 | 1 | 1 | 2014-08-27 | 2014-10-08 | -2 | 2014-10-12 | 2014-09-30 | 2014-09-30 | 2014-09-24 | [7 empty] | 2014-10-01 | 2014-10-08 | 2014-10-08 |  |  |  |  | 2014-09-23 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | [48 empty] | 2014-09-24
2 | 1 | 1 | 1 |  |  |  |  | 49 | Complete date Media Alert (One week prior to grad) | 1 | 1 |  |  | 2014-09-29 | 2014-11-13 | 2014-11-13 | 2014-11-13 | 2014-11-11 | 2014-11-11 | 2014-11-13 |  | 2014-12-02 | 2014-12-04 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-11-27 | 2014-11-11 | 2014-11-11 | 2014-11-11
1 | 1 | 1 | 1 |  |  |  |  | 50 | Schedule date to Create Press Release or Media Alert | 1 | 1 |  |  |  | 2014-10-08 | -2 | 2014-10-12 | 2014-09-30 | 2014-09-30 | -13 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-01 | 2014-10-08 | 2014-10-08 |  |  |  |  | 2014-09-23 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | [48 empty] | -13
1 | 1 | 1 | 1 |  |  |  |  | 51 | Who will complete task | 1 |  |  |  | Tere | Tere | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one |  | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one
3 | 1 | 1 | 1 |  |  |  |  | 52 | Use constant contacts for first email (Schedule Date) | 1 | 1 |  |  |  | 2014-10-08 | 2014-10-05 | 2014-10-12 | 2014-09-30 | 2014-09-30 | -13 | [7 empty] | 2014-10-01 | 2014-10-08 | 2014-10-08 |  |  |  |  | 2014-09-23 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | [48 empty] | -13
1 | 1 | 1 | 1 |  |  |  |  | 53 | Use constant contacts for first email (Actual Date Sent) | 1 | 1 |  |  |  |  | 2014-09-17 | [5 empty] | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10
1 | 1 | 1 | 1 |  |  |  |  | 54 | Date email sent to Dignitaries (Schedule Date) | 1 | 1 |  |  | 2014-08-27 | 2014-10-08 | 2014-09-30 | 2014-10-12 | 2014-09-30 | 2014-09-30 | 2014-09-24 | [7 empty] | 2014-10-01 | 2014-10-08 | 2014-10-08 |  |  |  |  | 2014-09-23 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | [48 empty] | 2014-09-24
1 | 1 | 1 | 1 |  |  |  |  | 55 | Date email sent to Dignitaries (Actual Date Sent) | 1 | 1 | [10 empty] | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10
1 | 1 | 1 | 1 |  |  |  |  | 56 | Date email sent to Media (Schedule Date) | 1 | 1 |  |  | 2014-08-27 | 2014-10-08 | 2014-09-30 | 2014-10-12 | 2014-09-30 | 2014-09-30 | 2014-09-24 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-01 | 2014-10-08 | 2014-10-08 |  |  |  |  | 2014-09-23 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 | [48 empty] | 2014-09-24
1 | 1 | 1 | 1 |  |  | 1 |  | 57 | Date email sent to Media (Actual Date Sent) | 1 | 1
2 | 1 | 1 | 1 |  |  | 1 |  | 58 | Date followed up on Press Release (using Network Solutions) (Schedule Date) | 1 | 1 |  |  | 2014-08-30 | 2014-10-08 | 2014-09-30 | 2014-10-12 | 2014-09-30 | 2014-09-30 | 2014-09-27 |  | 2014-10-01 | 2014-10-08 | 2014-10-09 | 2014-10-08 | 2014-10-03 | 2014-10-10 | 2014-10-04 | 2014-10-11 | 2014-10-11 |  |  |  |  | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | 2014-09-27 | [48 empty] | 2014-09-27
2 | [5 empty] | 1 |  | 59 | Date set for Graduation Invite (2 wks Prior. Trainers or designee perform task from office) |  | 1 | 1 |  | 2014-09-29 | 2014-11-17 | 2014-11-06 | 2014-11-06 | 2014-11-04 | 2014-11-04 | 2014-11-06 |  | 2014-11-25 | 2014-11-27 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-20 | 2014-11-04 | 2014-11-04 | 2014-11-04
1 | [5 empty] | 1 |  | 60 | Who will complete task | 1 |  | 1 |  | Tere | Tere | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one |  | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one | Dont have one
2 | 1 | 1 | 1 |  |  | 1 |  | 61 | Date to Follow Up to Invited Dignitaries | 1 | 1 |  |  | 41913 | 41956 | 41956 | 41956 | 41954 | 41954 | 41956 |  | 41975 | 41977 | 41974 | 41975 | 41976 | 41970 | 41954 | 41954 | 41954
6 | 1 | 1 | 1 |  |  | 1 |  | 62 | Date to Follow Up w/ Media Alert | 1 | 1 |  |  | 41913 | 41958 | 41957 | 41957 | 41955 | 41955 | 41957 |  | 41976 | 41978 | 41975 | 41976 | 41977 | 41971 | 41952 | 41955 | 41955
2 | 1 | 1 | 1 |  | 1 | 1 |  | 63 | Creation of Database |  | 1 |  | 1
1 |  |  |  |  | 1 |  |  | 64 | Intake of Applications |  |  |  | 1
1 |  |  |  |  | 1 |  |  | 65 | Administration of Entry Matrix - Compilation of Summary Results |  |  | 1 | 1
1 |  |  |  |  | 1 |  |  | 66 | Sign-in Sheet: update attendance |  |  | 1 | 1
2 |  |  |  |  | 1 | 1 | 1 | 67 | Report-out on class performance |  |  | 1 | 1
1 |  |  |  |  | 1 | 1 | 1 | 68 | Update percent complete on task list - review of students work |  |  | 1 | 1
20 |  |  |  |  | 1 |  |  | 69 | Teach Course |  |  |  | 1
1 |  |  |  |  | 1 | 1 |  | 70 | Call absent students |  |  |  | 1
| 1 | 1 | 1 | 1 | 1 | 1 | 1 | 71 | CASF Contract Management Service Provided but not Budgeted
4 |  | 1 | 1 | 1 | 1 | 1 |  | 72 | Quality Assurance Visits | 1 |  | 1
8 |  |  |  |  | 1 | 1 | 1 | 73 | Maintenance of Alumni Database | 1 |  | 1
40 | 1 | 1 | 1 | 1 | 1 | 1 |  | 74 | Perparation of Quarterly Reports for CASF Reimbursement | 1 | 1 | 1 | 1
4 | 1 | 1 | 1 | 1 | 1 | 1 |  | 75 | Tracking of outreach effors CM Calendars | 1 | 1
12 |  |  |  |  | 1 | 1 |  | 76 | Preparation of Ed/Grad Plan PowerPoint Presentations | 1 | 1
2 |  |  |  |  | 1 | 1 |  | 77 | Securing Graduation Location | 1 | 1 | 1
6 | [7 empty] | 78 | Update and Maintain NIU Website | 1
4 | [7 empty] | 79 | Prep. Sign-ins - mail hardcopy |  |  | 1 | 1
12 | 1 | 1 | 1 | 1 |  | 1 |  | 80 | Mass Email Blasts on Success Stories | 1
40 | 1 | 1 | 1 |  |  |  |  | 81 | Prep Grad Videos, TV, Newspaper Coverage, Social Media and Website Promotion | 1
293 | [7 empty] | 159 | Task-Touches By Role Played, By Site = 159 | 43 | 40 | 51 | 25
Sum Total Action within each ACTIVITY | 29 | 32 | 47 | 30 | 34 | 31 | 12 |  | Percentage of Hours By Role Played, By Site | 27.04% | 25.16% | 32.08% | 15.72%
Actual in Delivery of Contract | 13.49% | 14.88% | 21.86% | 13.95% | 15.81% | 14.42% | 5.581% |  | Hours By Role Played, By Site | 79.239 | 73.7107 | 93.9811 | 46.0692
Approved CASF Budget Percentages | 21% | 7% | 15% | 7% | 15% | 21% | 15%
[8 empty] | 57 | [5 empty] | 10/6/14 - PLAN: Coordinate Tmrw Make Up Session: Continue calls to alumni, DIS plan: researched & reviewed DIS Options: , Train Esteban, Yuliana9/11 - call jen, spoke w/ patricia- set up connect ed call9/4 - Sent all call script to Cianii-Bethune email follow up to patriicia 9/3 - schools all call system is down. parent center will make calls. 9/2 - coordinate all call 8/29- sent mou.8/29 -DJ follow up back to school nite. 8/28- DJ prep & coordinate back to school nite w/ Juan Carlos & Estaban.8/26 - Call Juan Carlos table 5-7, ask him abt the parent. Conf call DJ, LO w/Jen Reid & Patricias Navarro , they will try to find funding w/prinipal. sent flyer & db to jen.8/25 - Send MOU. Conference call tues. 8/26 @ 9 am, LO, NR 8/22/- Called- Not in today. LM 8/21 - DJ sent follow up email, flyer & conf call request. 8/20/- spoke w/ Jen new coordinator.who replaced amy chou would like classes asap. Teaser sample class scheduled 8/28 @ 4pm & 7pm .8/18: NR-Asked for our contact and she does not work there any more. | 10/8 - GOAL: DJ. Change Orientation Date to Tues 10/14/14 - Start Class Date Thur 10/16/14. Contact Jennifer to verify & coordinate, 145 Orientation letters need to be mailed by tmrw. Schedule Hortencia Friday @ 11 to begin follow up calls, Parent Interest List: Coordinate Flyer w/ Sheena / ACCOMPLISHED: Spoke w/ Jen, Revised schedule: update site task mgr, send email w/ update: , update calendar, notify Neri to change orientation letter. prep flyr request to send to Sheena & email, Assigned to Hortencia to create Database & make phone calls today. |  | 9/4- called principal-left msg, sent f/u email. 8/29 -DJ follow up back to school nite- Principal Galicia presented video to parents & 13 interested parent signed up, asked Magdalena to create a database & forward to office. 8/28- DJ prep coordinate back to school nite with Magdalena 8/26- Need Joacim to table at back to school nite @ 6pm. 5 min to present latest video, talk abt program. Sign ups. Invite parent, ask joacim parents name tall lady, light skinned, presenters to see if she can help @ table, shadow. 8/21 - Principal Galicia mtg w/LO tues. 8/26/14 @ 10:30am. Spring 2014 HN+T. Fall 2013 PE+T 20 parents @ $190 pd $3,800 | 10/9/14 - Tuesday orientation only 4 showed, called Monica all week unable to connect, Resend follow up email requesting conference call on friday | 10/9/14 - Tuesday orientation only 4 showed, called Monica all week unable to connect, Resend follow up email requesting conference call on friday | 10/9/14 - Goal: Set up conferenc all w/ Eydee, revise start date, revise flyer, get update from larry board mtg, contact silma FUSD. Accomplished, left eydee vm & sent follow up email, called Silma, she gave name of parent oonnect: Brandy Segul, she will contact me today. set for follow up tmre. 9/30 -DJ spoke with Eydee, Interest list of 5 people, will share with afterschool parents, will attend FUSD board meeting tmrw nite @6pm . MY Goal: get parents involved from Cypress Elementary & Fontana Middle School, they are closest to cypress center.. 9/26 - Spoke with Silma Navarro, she referred our info to her director as soon as shes gets a response she will forward it to me. RECOMMENDS: Attend Board Meeting on Wed 10/1/2014 @ 6PM in the interim. Dont need to be on the agenda, fill out an interest card upon arrival. 9/23 - Spoke with Eydee, Classes will be pushed out as follows: orientation Tues, 10/7 , start date Tues 10/14, end date Thur 11/6, grad date Thursday 11/13 @ fpm. 9/8/14 - Conference Call 9/11//14 @ 11am 9/4 - Sent all call script to Cianii-Bethune email follow up to patriicia 9/3 - schools all call system is down. parent center will make calls. 9/2 - coordinate all call 8/29- sent mou.8/29 -DJ follow up back to school nite. 8/28- DJ prep & coordinate back to school nite w/ Juan Carlos & Estaban.8/26 - Call Juan Carlos table 5-7, ask him abt the parent. Conf call DJ, LO w/Jen Reid & Patricias Navarro , they will try to find funding w/prinipal. sent flyer & db to jen.8/25 - Send MOU. Conference call tues. 8/26 @ 9 am, LO, NR 8/22/- Called- Not in today. LM 8/21 - DJ sent follow up email, flyer & conf call request. 8/20/- spoke w/ Jen new coordinator.who replaced amy chou would like classes asap. Teaser sample class scheduled 8/28 @ 4pm & 7pm .8/18: NR-Asked for our contact and she does not work there any more. |  | 9/11/14 - Set for follow up 9/15/14 Emailed recvd from Yesenia as follow: We have received the MOU and I have forward it to my director.I received notice that we will have to wait until this is approved by the board before we can meet with the principals and continue with the timeline. I will wait to hear from my director for further steps. Once approved I would want to have a meeting with all 6 site principals and their community liaisons so we may begin the process. Thank you for your patience. | 10/9/14 - Goal: Send Flyer request to Sheena | 10/9/14 - Goal: Send Flyer request to Sheena | 10/9/14 - Goal: Send Flyer request to Sheena |  | 10/9/14 - Goal: Send Flyer request to Sheena |  | 10/9/14 - Goal: get parent list (150) today. Accomplished: Called in am & this afternoon, spoke w/ Marilyn office mgr. emailed both contacts/ Spoke w./ Principal Sims will get us the list tonight. | 10/9/14 - Goal, get status of number of enrolled from principal haro, disuss changing start date if necessary. Accomplished: Called twice & sent follow up email twice, set for follow up tmrw | 10/20/14 - phone call & email to carolina | 10/20/14 - follow up phone call to veronica & f/u call & email principal altamirano, DJ |  | amy helped us get into OceanView School District | 8/29 DJ - Called Principal Minjas, spoke w/ Reina shes in a mtg, lm. Send email. | 8/29 - Called New Principal - Unavailble, send email, NOTE: Winter 2014 under prior principal QSTE 20 parents @ $90, $1800. classes started 2/14/14 | 8/29 - DJ - Called, new principal Alejandro Reed - Principal or office mgr is not in today. Call back monday. | 3 sessions PE+T prior principal |  |  | 9/25 - Sent follow up email to Beatrice, cc'd principal maravilla & julieta mendoza, giving quotes for both QSTE & Advanced Courses. DJ. Spoke with Beatrice will forward to Principal. Called Julieta, call back after 1 pm . DJ..9/4 - set for follow up on 9/8 & 9/10 8/29 -DJ Follow Up w/Beatrice. Resend MOU she did not receive it. 8/25 - LO will send mou to beatrice to present to principal & board members 8/22- Call back in 20 min. 8/21 DJ-left msg. Follow Up call, must be board approved Next Board Mtg Sept 10 potential for classes starting October ,8/18/14 DJ- Spoke w/ Beatriz, she will relay msg to principal & call us back. they pd full PE+T -30 parents $5,700. offer $90@ 25 parents $2,250 - 5 parents free | 8/27 - LO met w/ John - Teachers Union & Claudia - Its a go for Garey. Need to Send MOU | 8/27/15 - LO met w/ John Teachers Union. will get principals info to send intro package | 8/27/15 - LO met w/ John Teachers Union. will get principals info to send intro package | 8/27/15 - LO met w/ John Teachers Union. will get principals info to send intro package | [7 empty] | 8/21 - DJ Sent flyer to Renee Barbee Nueva Voz | Last Yr 20 parents QSTE @ $20 | Last Yr 20 parents-QSTE @ $20 | 8/22 DJ - Spoke w/ Veronica, gave name of Silvia Cervantez PTA Lead, will call back on monday w/detailed info. Last Yr 30 parents-QSTE @ $20 | 9/30 esl class - tomorrow will get more sign ups. as of now only has 2 interested. Neri quoted $20 - Maria says there is no money in budget parents will have to pay. She will call neri or i tomorrow to give results. not open to so orientation letters. |  | 9/26 - Parents will have to pay $25 they have no funding in budget. would like us to present at parent meeting on thurday 8:30, need flyer |  |  | 8/27- Not in budget, will not know funding until October 2014 8/26 - DJCalled. No Anser- Send Follow Up Email, 8/18: NR-Talked to Ms. Martinez, she is interested an wants to see her budget for $90 for 15 parents. Contact her next week. |  |  | 8/27 - Received Email from Juan Perez, principal is unable to fit into budget at this time. Sent follow up email to Amparo Mendoza. 8/26/- snt email to juan perez 8/25 recvd email frm juan perez, school contact. 8/22- DJ 8/21 - DJ Called no answer 8/20/14- DJ called no answer - sent follow up email. 8/18/14 - DJ. Juan Perez. Would like to have new class, gave him the schedule, he will talk to the principal & get back to us. | 8/22 - DJ- Called Diana & Principal Velasco left msg to call back. 8/20- DJ - Diana has a meeting tmrw w/ Principal Velasco 8/18/14 - DJ-Spoke with Diana Guillen, will talk to Principal Velasco, they do have a little funding avail. call her back Wed. |  |  |  |  | 9/3/14 - called Alex, asked me to resend. follow up tommorrow | 8/27 - NR Parent Mtg - 9/4/14 |  |  | Summer 2013 30 parents full PE+T | 8/21 - DJ Sent Initial Contact Email to principal Gonzalez & cc Parent Ramona Alvarez | 8/21 - DJ Sent Initial Contact Email to Lori Cervantes Community School Liason |  | 9/3/14 - called left a message with Monica regarding start up new classes. |  |  |  | 8/21 - DJ - Called spoke w/Lena will give Lilia unavail will leave msg, send follow up email as well. Last yr @ Monte Vista, PE+T 25 parents @ $190, district pd $4,750 | 8/22 DJ- follow up call to principal. not in yet. 8/21 -DJ - Left voicemail for principal Gonzales |  |  |  |  | 8/21 - DJ Left VM for principal Alonzo Last Yr @ Suva, 60 parents -QSTE @ $20 |  | 9/26 - not in budget, havent had parent interest either. Discussed quarter possiblity of doing classes, recommended collaborating with surrouinding schools as a parent resource. | 9/4 - Sent Draft MOU to Beatriz 9/3 - spoke with Beatriz, to facilitate Train the Trainer starting next week. Also she will speak to new principal about continuing new classes, they have a budget. Sent email
Formulas:
LAUSD A = [LAUSD A, row below]-1
LAUSD B = [LAUSD B, row below]-0
QSTE = [QSTE, row below]-2
West Covina USD = [West Covina USD, row below]-2
Inglewood USD = [Inglewood USD, row below]-2
City of Fontana = [City of Fontana, row below]-2
Anaheim City School District = [Anaheim City School District, row below]-2
T, W, Th 3-6 pm = [T, W, Th 3-6 pm, row below]-2
APCH = [APCH, row below]-2
T,W, Th 2-5 pm = [T,W, Th 2-5 pm, row below]-2
Huntington Beach = [Huntington Beach, row below]-2
Note on Q26: Must confirm with Mr Tapia
Note on P32: Will get updted once we got the list of parents from school (NR. If their system is back up this week.
Note on Q39: Calls are still being made by Hortensia -Neri Rivas